## Outputs
LP | • Report on key findings resulting from interregional exchange activities & relevant materials after project meetings in Catalonia
P2 | • Report on key findings resulting from interregional exchange activities & relevant materials after project meetings in Emilia Romagna
P4 | • Report on key findings resulting from interregional exchange activities & relevant materials after project meetings in Lubelilskie
P5 | • Report on key findings resulting from interregional exchange activities & relevant materials after project meetings in East Flanders
P3 | • Report on key findings resulting from interregional exchange activities & relevant materials after project meetings in Lithuania
LP | • 7 Meeting Reports with Key Regional Stakeholders
P1 | • 7 Meeting Reports with Key Regional Stakeholders
P2 | • 7 Meeting Reports with Key Regional Stakeholders
P3 | • 7 Meeting Reports with Key Regional Stakeholders
P4 | • 7 Meeting Reports with Key Regional Stakeholders
P5 | • 7 Meeting Reports with Key Regional Stakeholders
P2 | • 1 Methodology Brief for Regional Co-Evaluation
LP, P2, P5 | • 3 Interregional Peer review reports
LP | • 1 Interregional analysis report with a shared analysis of gaps, strengths & opportunities for policy change in the EU resulting from co-evaluation findings and peer review discussions of partnering regions, as well as a joint survey and exchange actions with other EU regions
P4 | • 1 Methodology Brief for GP collection
• 1 Interregional Benchmark of Good Practices (18 GP)
P3 | • 1 set of Terms of Reference for Interregional Thematic Workshop facilitation
P3, P5, P6 | • 3 ITW reports
P4 | • 1 Methodology Brief for Targeted Study Visits
LP | • Targeted Study Visits report
All PP | • 6 Regional Action Plans

## WP
[10 empty] | P7 (ZSI) | Other Communication
|  |  |  | P1 - GENCAT | P2 - MBOC | P3 -LIC | P4 - POLAND | P5 - EVEC | P6 - LOWER
Semtester 1 | RP1 | M1 | March 2019 | RSG1 | RSG1 | RSG1 | RSG1 | RSG1 | RSG1
KICK-off
Study visit
Steering Group 1
|  | M2 | April 2019
|  | M3 | June | RSG2 | RSG2 | RSG2 | RSG2 | RSG2 | RSG2
|  | M4 | July
|  | M5 | August
|  | M6 | September |  | IPeR 2nd round
Study visit
[5 empty] | Steering Group 2 | [5 empty] | eNewsFlashes
Semester 2 | RP2 | M7 | October | RSG3 | RSG3 | RSG3 | RSG3 | RSG3 | RSG3
|  | M8 | November
|  | M9 | December
|  | M10 | Jan 2020
|  | M11 | 2020-02-01 |  |  |  |  | IPeR 3rd Round |  | INTERREGIONAL ANALYSIS
Study visit
Steering Group 3
|  | M12 | March 2020 | RSG4 + dissemination | RSG4 + dissemination | RSG4 + dissemination | RSG4 + dissemination | RSG4 + dissemination | RSG4 + dissemination |  | eNewsFlashes
Semester 3 | RP3 | M13 | April 2020
|  | M14 | May
|  | M15 | June |  |  |  | Study visit
ITW 1
Steering Group 4
|  | M16 | July
|  | M17 | August
|  | M18 | September | RSG5 | RSG5 | RSG5 | RSG5 | RSG5 | RSG5 |  | eNewsFlashes
Semester 4 | RP4 | M19 | October
|  | M20 | November | Study visits until M25 |  | Study visit
ITW2
Steering group 5
|  | M21 | December
|  | M22 | January 2021
|  | M23 | February 2021
|  | M24 | March 2021 | RSG6 | RSG6 | RSG6 | RSG6 | RSG6 | RSG6 |  | eNewsFlashes
Semester 5 | RP5 | M25 | Apr | [5 empty] | Steering Group 6
|  |  | May | [5 empty] | Study visit
|  |  | June | [5 empty] | ITW3
|  | M26 | July
|  | M27 | August | RSG7 | RSG7 | RSG7 | RSG7 | RSG7 | RSG7
|  | M28 | September
|  | M29 | October
|  | M30 | November
|  |  |  | Dissemination event | Dissemination event | Dissemination event | Dissemination event | Dissemination event | Dissemination event |  | eNewsFlashes
M1
M2
M3
M4
M5
Semester 6 |  | M6
M7
M8
M9
M10
M11
Semester 7 |  | M12
M13
M14
M15
M16
M17
Semester 8 |  | M18
M19
M20
M21
M22
M23
Semester 9 |  | M24 |  | Final Conference PHASE 2